## Priority Stories
Epic# | Story# | Details | FE or Both | Present Implementation | New Changes | Service Imacted | Assumptions/Dependency | Sprint | Estimatet(man days) | Owner
DCNG-244 | DCG2-1300 | resource lifecycle management- 1. Able to create a resource (image) outside of a project 2. Able to import a resource into more than one project 3. After a resource (image) is imported into a project, it is set to assigned status in "My library" 4. Resource can be deleted only after unassigning from all projects 5. When project is deleted, the project gets automatically unassigned from the resource in "My Library" | Both | in current implementation we cannot create resource/container without mapping it to project/application. Also we don’t maintain any status when container is assigned to a project /application. Currently container can be deleted eventhough it is assigned to a application and project | BE:- Most of the functionality already exists. Requires controller name changes FE: url changes | Byoc-ms Configuration-ms Byos-ms | Byos implementationhas to be taken care by the ciurent developemnt team. Container multi project mapping implementation. Project level labelling is currently not supported. Require clairity on filter functionality on the my library page |  | BE(1) + Fe(2)
| DCG2-1873 | "Project" lifecycle management Allow user to create a project 2. Once project is created, user can save the project configurations 3. User can edit project configurations from MyLibrary -> Project 4. All the results, logs, and labels will persist only when the project exists. 4. When the project is deleted, all the results, logs will be deleted from filesystem, after a confirmation msg 6. When a project is deleted, project database entries - project name, project description, tag, container name will be deleted from database entry and UI 7. Container image in the resource library will be unassigned from this project. | Both | configuration is add as part of create container screen.create container Api takes care of adding configuration as well in config tables. currently when we delete project results do not get deleted. Point 6 iand 7 s already in place currently | Api to update and add configuration already exists we need to refine it. Ordering of container needs to be taken care of, api already exists in multicontainer same needs to be integrated/modified to handle order request structure. One container mapped to different project with different configuration is missing at the moment, new implementation to take care of that shuld be written. Radio button/checkbox functinality to add dependent container implementation has to be added There are 2 configuration screens Project level configuration and container level configuration. Project level configuration also maintains container execution ordering Rename in DB and classes tags to labels. delete results when projects is delted reset assigned status of resource to default when project is deleted. | Byoc-ms Configuration-ms | Api to add/update configuration as per new screen already present |  | 5(BE) + 3(FE)
| DCG2-1794 | Quick dashboard, library and filesystem access to returning users 1. The dashboard, library and filesystem are viewable at all times independent of the project and resource import flows 2. Dashboard will show the status of all executing and executed projects at any point. 3. Library will show the status of all projects created and all resources( container images) built/ imported and saved in OCR 4. Filesystem will show the view for all files located in user's volume mount 5. Users can view the dashboard, library, filesystem from any screen and this information will persist till the user's account is active | Both | Dashboard displays Project->Application->container details and status is shown through a get api using container Id in get request | New changes all the result should be aggregated per user and returnd through single API. Currently we are retuning it per application basis. New Feature:- Currently Multi-container feature does not send the aggregated status of all conatiner under an application, this needs to be changed to accomadate for aggregated status. | Byoc-ms | New functionalities which are WIP should make sure thay are updating status in Pod status table simmilar way existing functionality is working. Search Fubctionality will remain as it is with no additional Keys. Sort:- require clarification for new UX/Pagination is a new implementation |  | 3(BE) + 6(FE-excluding sorting and search only layout changes + once sorting is clarified we wcan include with additional effort)
| DCG2-1789 | Change Project->Application->Resource hierarchy to Project->Resource | Both | currently project and appplicatin are assocaited though user id and project id and have simmilar screens | DB Clean Up: Tables Impacted:gen2_project_library (stop using this table), gen2_application(renamed to Gen2_Project delete project_Id column),gen2_application_container(rename to gen2_project_container, cjhange column names) Java Application and model related refactoring in context to project Java Entity refactoring corresponding to table changes. Java entity method reference changes. Create Application MS Url change same as CReate project. Get Application MS url changes in context to project. FE:- remove application hierarchy(1) and align to new flow(3), API integration with new HIerarchy(1) | Byoc-ms Helm-ms Configuration-ms Byos-ms |  |  | 7(BE) + 5(FE)
Total=16(BE) + 16(FE)

## Future Implementation
Epic# | Story# | Details | FE or Both | Present Implementation | New Changes | Service Imacted | Assumptions/Dependency | Sprint | Estimatet(man days) | Owner
| DCG2-1903 | [Edit Project] Allow user to re-configure the container runtime parameters by storing previous inputs. 1. All resource parameters ( Image URL, image name, container name, runtime configurations) are saved in the project 2. These can be edited anytime later, from MyLibrary ->Project -> Configure 3. The last edited configuration is preserved
| DCG2-1294 | Intuitive user experience- Asynchronus call handling in UI | FE Only |  |  |  | Genereic and future implementation | common Changes:
| DCG2-1301 | [Logging] User can view Devcloud logs per container from dashboard | Both |  |  |  | Future Implementation
| DCG2-1790 | 1. Maintain the states Creating ->Created -> Running -> terminated |  |  | Not enough details available on the story
| DCG2-1791 | Create appropriate Project states:1. Maintain the states Created -> Scanning -> (Scanning error) -> Queued -> Running -> Completed |  |  | Future implementation
| DCG2-1792 | User session timeout 1 hour after being idle 1. If the project is in completed state for more than one hour, user's session will end |  |  | Future Implementation
| DCG2-1793 | Provide the queue number to the user when the jobs are queued up |  |  | Future Implemntation
| DCG2-1795 | Display all created (My library) and executed (Dashboard) projects |  |  | Need more clarity |  | please confirm from where labels are coming at project level. Currently label/tag is maintained at container level.
| DCG2-1898 | [MyLibrary] Size of each image is displayed under images tab |  |  | future implementation currently image size is not getting calculated
| DCG2-1899 | display man page to provide all the command line options to the user |  |  | New implementation for CLI will take care of it.
| DCG2-1900 | [Filesystem] User can view their persistent storage in MyLibrary |  |  | future implementation, functionality does not currently exist
| DCG2-1902 | [Edit Build config] Allow user to re-configure the build parameters by storing the previous inputs |  |  | New feature implementation/ Story requires more details
| DCG2-1914 | Manage container runtime operations and dependencies 1. Individual Containers can we stopped, restarted, deleted from the dashboard. 2. This may change the runtime behaviour of the other containers in that project but this is for the user to manage. | Both | Container can be terminated only | Container stop / restsrt / delete from OCP feature is unavailable
| DCNG-261 | [Dashboard fields] Support the new fields in the dashboard. The dashboard fields will be in line with the finalized wireframes https://xd.adobe.com/view/c7570613-aaba-4274-978d-b30db3d54207-9204/ | FE Only
| DCNG-262 | [Library fields] Support new fields in "My library" The Library fields will be in line with the finalized wireframes https://xd.adobe.com/view/c7570613-aaba-4274-978d-b30db3d54207-9204/ | FE Only |  | Dupplicate of DCNG-261
| DCG2-1917 | [OCR import] Resources imported to OCR will appear in Mylibrary ->resources |  |  | Future implementation
| DCG2-1918 | [Logging] User can view build logs per image in My library -> images |  |  | Future Implementation
| DCG2-1948 | Container name is the unique identifier for a resource. |  |  | Future Implementation
| DCG2-1949 | 1. The number of nodes on which user can schedule the jobs is limited to 3. 2. The design should be such that this number is configurable and can be changed at a later point when we make a data driven decision 3. All the concurrent executions can be viewed in the dashboard. |  |  | Future Implementation
| DCG2-1950 | Limit the number of simultaneous builds by a user to 3 |  |  | Future Implementation
| DCG2-1951 | If the older build was assigned to a project, during the next deployment, project will take the latest build. After assigning a built image to a project, if the user has re-built it, when launching the project subsequently, the new image will be taken. |  |  | New Feature
| DCG2-1952 | [Queueing] User should be able to queue their jobs |  |  | Future implementation
| DCG2-1953 | [Session time] Provide a node wall time of 2 hours
| DCG2-1954 | Graceful transition from Create project -. Launch -> Dashboard |  |  | More description required

## sheet4
FE Only
Both